## Sheet1
YM-SAJCO JV CTW 130 SADARA RAIL PROJECT & JUBAIL RAILWAY NETWORK PROJECT
Request for Inspection (RFI)
Project Name: | [6 empty] | RFI Ref. No:
[7 empty] | Subsection: | TestSubsection2
Consultant: | [6 empty] | Station: | Middle of part C08 KM: 1+046.473 - 1+104.974
Contractor: | [6 empty] | Date: | 2.08.2020
Description of the Activity: |  |  | Earthworks |  | Drainage | Structure | Track | Utilities | S&T | Roadwork |  | Others
Alumina-thermite welding production
Ultrasonic Test for Each Weld
| Location: | TestSubsection2
Middle of part C08 KM: 1+046.473 - 1+104.974
.
Work Permit Approved Code:
Work Method Statement: |  |  | CTW130-SJR-TYP-YMS-MS-ATW-0035 -REV.02
CTW130-SJR-TYP-YMS-MS-UTI-0039-REV.01
Approved Drawing reference: |  |  | CTW130-SYS-DV-TRA-DWG-4658 to 4666
Inspection Level (as per ITP): |  |  |  | Hold Point |  |  | Inspection |  |  | Witness
Requested Inspection Date: | [6 empty] | Requested Inspection time (approx.):
Previous Activity finished: |  |  | Final Stage Lifting
Contractor's Engineer:
Name: |  |  |  | Position: |  |  |  | Signature: |  |  | Date:
The Related Engineer that signs, certifies that these works have been executed in accordance with the Contract Requirements and Approved Drawings
Supervising Consultant's Inspection Report:
Approved (next activity may proceed)
Approved with Comments (next activity may proceed to incorporation of comments and resubmit again this format)
Rejected (revise and resubmit, next activity cannot proceed)
Supervising Consultant Representative:
Name: |  |  |  | Position: |  |  |  | Signature: |  |  | Date:
Acceptance does not relieve the Contractor from his responsibility and liability concerning compliance with the Contract Requirements

## Sheet3
File Name | Subsection: | Station: | Date: | Activity1 | Activity2 | Work Method Statement1 | Work Method Statement2 | Approved Drawing reference: | Previous Activity finished:
Alumina-thermite welding production_Middle of part C08 KM: 1+046.473 - 1+104.973 | P03 | Middle of part C08 KM: 1+046.473 - 1+104.973 | 2020-08-01 | Alumina-thermite welding production | Ultrasonic Test for Each Weld | CTW130-SJR-TYP-YMS-MS-ATW-0035 -REV.01 | CTW130-SJR-TYP-YMS-MS-UTI-0039-REV.00 | CTW130-SYS-DV-TRA-DWG-4658 to 4665 | Final Stage Lifting